## Sample Product Launch Timeline
SAMPLE PRODUCT LAUNCH TIMELINE
Need help? Register for a strategic consultation to talk through your product launch strategy.
|  | 2019 |  |  | 2020
Task | Notes | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Product Launch Date | “Product” (needs further defining) is ready to sell | bar: 2020 May
PRE-LAUNCH PLANNING & GOALS
Amass Screenshots of New Product | Start creating pitch deck for sales team. | bar: 2019 Oct to 2019 Dec
Set Launch Goals | Upgrade X% of client base by EOY, Pre-sell X number of licenses by launch date, Sell X number of new products by EOY. | bar: 2019 Nov
Migration Plan | You'll want a plan as to how existing clients migrate to the new tool, and when. | bar: 2019 Dec
Pricing & Promotions | This is a good time to adjust pricing. Consider price increase while the marketplace has context for the old vs. new. Also consider pre-launch purchase incentives to get new customers on board before launch. Consider promotional strategy to incentivize customers to buy and migrate.
LAUNCH
Begin Teasing to Existing Customers | Leverage screenshots/sales sheets. | bar: 2019 Dec to 2020 Apr
Market to New Customers | Leverage screenshots/sales sheets to begin selling to new customers. | bar: 2020 Jan to 2020 Apr
Create Mock New Product Demo | Does not have to be complete, just a "mock" demo for sales team. Full demo complete by launch. | bar: 2020 Jan
Beta Test | Beta test to best customers. They will be the most excited, and most forgiving. You'll need feedback, testimonials, accolodes to build confidence in the marketplace. Opportunity to launch with case study. | bar: 2020 Jan to 2020 Apr
Website Launch Featuring New Product | Launch new site at customer event. | bar: 2020 May
Full Demo, Intro Video | This is the perfect time to create a video launching the new product, leading to a full demo (to be facilitated by sales team). Launch video at customer event. | bar: 2020 Apr
PR & Advertising Push | No external PR until the product is ready to deliver. | bar: 2020 May to 2020 Jul
Onboarding | bar: 2020 May to 2020 Dec

## Blank Product Launch Timeline
BLANK PRODUCT LAUNCH TIMELINE
Need help? Register for a strategic consultation to talk through your product launch strategy.
|  | 2019 |  |  | 2020
Task | Notes | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Product Launch Date
PRE-LAUNCH PLANNING & GOALS
LAUNCH